## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-01 | As a developer, I want to set up the project environment with JDK, Spring Boot, MySQL, and Git so that development can begin smoothly. | MUST HAVE | None | Akhila | Completed
S1 | S1 | US-02 | As a user, I want to create, update, and delete tasks so that I can manage my daily work. | MUST HAVE | US-01 | Akhila | Completed
S1 | S1 | US-03 | As a user, I want to view all my tasks in a table format so that I can see task details clearly. | MUST HAVE | US-02 | Akhila | Completed
S2 | S2 | US-04 | As a user, I want pagination so that large task lists are easy to navigate. | MUST HAVE | US-03 | Akhila | Completed
S2 | S2 | US-05 | As a user, I want to filter and sort tasks by status, priority, and due date for better organization. | MUST HAVE | US-04 | Akhila | Completed
S2 | S2 | US-06 | As a user, I want to view tasks in a card view with flip animation for a better UI experience. | SHOULD HAVE | US-03 | Akhila | Completed
S2 | S2 | US-07 | As a user, I want a calendar view to visualize tasks based on due dates. | SHOULD HAVE | US-05 | Akhila | Completed
S3 | S3 | US-08 | As a user, I want to register and log in securely so that my tasks are private. | MUST HAVE | US-01 | Akhila | Completed
S3 | S3 | US-09 | As a user, I want OTP-based email verification for secure account activation. | MUST HAVE | US-08 | Akhila | Completed
S3 | S3 | US-10 | As a user, I want session-based access so only logged-in users can access tasks. | MUST HAVE | US-08 | Akhila | Completed
S3 | S3 | US-11 | As a user, I want to manage my profile and upload a profile picture. | SHOULD HAVE | US-08 | Akhila | Completed
S4 | S4 | US-12 | As a user, I want deleted tasks to move to a bin so I can restore them if needed. | SHOULD HAVE | US-02 | Akhila | Completed
S4 | S4 | US-13 | As a user, I want to export tasks as a CSV report and receive it via email. | COULD HAVE | US-09 | Akhila | In Progress
S4 | S4 | US-14 | As a user, I want to see a live world clock in the dashboard for better time awareness. | COULD HAVE | None | Akhila | Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint-1
US-01 | T-1 | Setup JDK,IDE, | 2026-11-27 | 2026-11-27 | Akhila | Setup | completed | 4
US-01 | T-2 | Create Spring Boot Project | 2026-11-27 | 2026-11-28 | Akhila | Setup | completed | 6
US-02 | T-3 | Design Task entity&repository | 2026-11-28 | 2026-11-29 | Akhila | Coding | completed | 5
US-02 | T-4 | Implement Creat & Update Task | 2026-11-29 | 2026-11-30 | Akhila | Coding | completed | 6
US-02 | T-5 | Implement Delete Task | 2026-11-30 | 2026-11-30 | Akhila | Coding | completed | 3
Sprint-2
US-03 | T-6 | Add pagination logic | 2026-12-01 | 2026-12-02 | Akhila | Coding | completed | 5
US-03 | T-7 | Add filters & Sorting | 2026-12-02 | 2026-12-03 | Akhila | Coding | completed | 6
US-04 | T-8 | Implement Table View | 2026-12-03 | 2026-12-03 | Akhila | UI | completed | 3
US-04 | T-9 | Implement CardView+ Flip | 2026-12-04 | 2026-12-05 | Akhila | UI | completed | 7
US-04 | T-10 | Implement Calender View | 2026-12-05 | 2026-12-06 | Akhila | UI | completed | 5
Sprint-3
US-06 | T-11 | Implement login &security | 2026-12-11 | 2026-12-12 | Akhila | Security | completed | 8
US-07 | T-12 | User Registration | 2026-12-12 | 2026-12-13 | Akhila | Coding | completed | 6
US-08 | T-13 | Profile Page +Image Upload | 2026-12-13 | 2026-12-14 | Akhila | UI | completed | 7
US-09 | T-14 | OTP &Email Integration | 2026-12-14 | 2026-12-15 | Akhila | Automation | completed | 6
Sprint-4
US-10 | T-15 | CSV Export &Mail Report | 2026-12-26 | 2026-12-27 | Akhila | Automation | completed | 66
US-11 | T-16 | Bin(Soft Delete &Restore) | 2026-12-27 | 2026-12-28 | Akhila | coding | completed | 5
US-12 | T-17 | World Clock&UI Polish | 2026-12-28 | 2026-12-29 | Akhila | UI | completed | 4
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7